## Dark
PROJECT: HealthFlow Connect
T1 Batch | [5 empty] | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
112103016, 112103028, 112103030
Project start date: | 2024-01-20 | [5 empty] | January | [13 empty] | February | [27 empty] | March | [30 empty] | April
Scrolling increment: | 0 | time axis 2024-01-20 to 2024-04-10
Task | Category | Assigned to | Completed By | Progress | Start | Days | time axis 2024-01-20 to 2024-04-10
Initiation
Characterizing the Issue Domain | High Risk | ALL | ALL | 100% | 2024-01-20 | 3
Articulating the Problem Description | Med Risk | Vipul Chaudhari | Vipul Chaudhari | 100% | 2024-01-23 | 2
Pinpointing Dependencies | Milestone | Aditya Choudhary | Aditya Choudhary | 100% | 2024-01-25 | 3 | bar: 2024-01-25 to 2024-01-27
Project Boundaries | Milestone | Ayush Ambhorkar | Ayush Ambhorkar | 100% | 2024-01-26 | 3 | bar: 2024-01-26 to 2024-01-28
Specifying Operational Requirements | High Risk | Aditya Choudhary | Aditya Choudhary | 100% | 2024-01-29 | 2
Recognizing Limiting Factors |  | Vipul Chaudhari | Vipul Chaudhari | 100% | 2024-01-29 | 2
Planning and Design
Gantt Chart Composition | Med Risk | Ayush Ambhorkar | Ayush Ambhorkar | 100% | 2024-01-31 | 2
Process Model Recognition | High Risk | Aditya Choudhary, Ayush Ambhorkar | Aditya Choudhary, Ayush Ambhorkar | 100% | 2024-02-02 | 1
Tech Infrastructure Identification | High Risk | Aditya Choudhary, Vipul Chaudhari | Aditya Choudhary, Vipul Chaudhari | 60% | 2024-02-03 | 3
Software Requirement Specification | High Risk | Vipul Chaudhari, Ayush Ambhorkar | Vipul Chaudhari, Ayush Ambhorkar | 0% | 2024-02-05 | 5
Data Flow Diagram | Low Risk |  |  | 0% | 2024-02-10 | 2
ER Diagram | Low Risk |  |  | 0% | 2024-02-10 | 2
UML | Med Risk |  |  | 0% | 2024-02-12 | 5
Backend Development
Preliminary Configuration | Low Risk |  |  | 0% | 2024-02-17 | 2
Crafting Routing Structures and Controllers | High Risk |  |  | 0% | 2024-02-19 | 15
Debugging Tool for Evaluation (Postman) | Milestone |  |  | 0% | 2024-03-05 | 3 | bar: 2024-03-05 to 2024-03-07
Frontend Development
Preliminary Arrangements | Low Risk |  |  | 0% | 2024-03-08 | 2
Establishing Communication between Backend and Frontend | High Risk |  |  | 0% | 2024-03-09 | 3
Designing the Foundation of the Web Page | Med Risk |  |  | 0% | 2024-03-11 | 10
Upgrading Design Elements Using Bootstrap | Low Risk |  |  | 0% | 2024-03-21 | 5
Integration of Complete Web Structure | Goal |  |  | 0% | 2024-03-26 | 7 | 2024-03-26: 2; 2024-03-27: 2; 2024-03-28: 2; 2024-03-29: 2; 2024-03-30: 2; 2024-03-31: 2; 2024-04-01: 2
Testing
On site real time testing | Med Risk |  |  | 0% | 2024-04-02 | 3
Feedback analysis | On Track |  |  | 0% | 2024-04-03 | 2
Doing necessary changes | On Track |  |  | 0% | 2024-04-05 | 6